## Sheet1
Report Date | Reported By | Priority | Status | Assigned To | Short Description | Expected Results | Actual Results | Steps to Reproduce
2024-03-03 | Andrew | P2 - Serious, game not working as expected | Resolved | Andrew | Player will stuck to top/bottom bound when player touched the bound | Player should be trap within the bound buy still able to leave the bound | Player will be stuck to the top/bottom bound | Move player until it reach/the top or bottom
2024-03-04 | Annie | P3 - Annoying, could ship but loss of marks | Resolved | Andrew | Player can go beyond the "floor" and onto the wall | Should not be able to go "top" and onto the backgorund's wall | Can go "north" and go onto the wall | Move upwards towards the wall and keep going
2024-03-05 | Annie | P5 - Minor or Feature that would be nice to have | In-Progress | Annie | Score displays over top of help menu | Help menu covers all of the components of the game | Help desk is covered by the score counter. | Press 'H' and observe.
2024-03-05 | Andrew | P5 - Minor or Feature that would be nice to have | Resolved | Andrew | health bar will go over the bullet | Bullet will rendered above the health bar | health bar will rendered on the bullet | Shoot to the health bar
2024-03-05 | Andrew | P5 - Minor or Feature that would be nice to have | Won't Fix | Kush | Backgound music will continue to play even the player is dead | I might be better if the backgound music pause when player is dead | Music will continue to play | Let the player die
2024-03-05 | Andrew | P5 - Minor or Feature that would be nice to have | Won't Fix | Andrew | Minion will not collide with each other. It's kinda like a feature because Brotato (propular 2D shooting game) also do it in this way. | I can make minion collide if it's required | Minion will overlay on each other | try to group minion by moving in circle
2024-03-22 | Vicky | P3 - Annoying, could ship but loss of marks | Resolved | Andrew | Minions will keep flashing when they overlap on bullet/power up | Should overlap normally and should not keep flashing | Overlap each other, but flashing | might be something related to order for rendering
2024-03-22 | Andrew | P3 - Annoying, could ship but loss of marks | Resolved | Andrew | Roamer's speed some time will be super fast/slow | Roamer have a speed range | Roamer will be have a very different speed | let roamer hit the boundary
2024-03-23 | Andrew | P2 - Serious, game not working as expected | Resolved | Andrew | Player sometimes can be stuck in the wall if it stay there for too long | Player should not be stuck in the wall | Player will be stuck in the wall | Keep moving player to boundary for 3 seconds
2024-03-24 | Andrew | P3 - Annoying, could ship but loss of marks | Resolved | Andrew | Health bar will go over the frame if health is too large | health bar should be contanted within the health frame | health bar will go over the frame if player health is >100 | set player health to different value
2024-04-06 | Annie | P3 - Annoying, could ship but loss of marks | Resolved | Annie | Bullets and powerups display overtop of cutscenes | nothing should render over top of the cutscenes | bullets and powerups over cutscenes | shoot bullets as the cutscenes are begining
2024-04-07 | Andrew | P4 - Annoying/Limiting but could ship as is | Won't Fix | Andrew | player will keep recieveing the key borad input (super rare case)even no been pressed | Key input recieve normally | Key input will keep input(player keep moving in a direction) | Not sure, but when it occur, just press the key in the same direcation and it will fix this issue
2024-04-08 | Andrew | P4 - Annoying/Limiting but could ship as is | Won't Fix | Eddie | Boss is using AABB collision | Boss is using mesh | Boss use AABB | Shoot to boss
2024-04-08 | Andrew | P4 - Annoying/Limiting but could ship as is | Won't Fix | Andrew | Split force to strong when the enemy get too cloose | Split force should be mild | Split force to strong when the enemy get too clooseo strong when the enemy get too cloose | Try to make two enemy really close
2024-04-08 | Andrew | P4 - Annoying/Limiting but could ship as is | Won't Fix | Andrew | Some super minior layering issue, when the enemy get too cloose | No layering issue. | Some layering issue | try to get enemy close
2024-04-09 | Annie | P5 - Minor or Feature that would be nice to have | Won't Fix | Annie | Powerups are able to render on top of each other. | Expected that there be some jitter with the powerups so that the powerups generate evenly throughout the game board. | Powerups are able to layer on top of each other. | Play the game for a long enough time, and observe how the powerups generate.